## PTL
Performance Testing Processes (Life Cycle)
# | Steps | Description
1 | Requirement Gathering & Analysis | Identify performance goals, including response times, throughput, and resource utilization. Understand the application's architecture, user load, and expected usage patterns. | Completed
2 | Planning and Design (Plan and Design Performance Tests) | Create a performance test plan outlining the scope, objectives, testing approach, and environment setup. Define performance test scenarios and workload models based on user behavior. | Completed
3 | Environment Setup | Prepare the test environment, ensuring it mirrors the production environment as closely as possible. Configure necessary hardware, software, and network settings. | Completed
4 | Tool Selection | Choose appropriate performance testing tools (e.g., JMeter, LoadRunner, Gatling) based on the application and testing requirements. | Completed
5 | Test Script Development (Implement Test Design) | Develop performance test scripts simulating user actions and load scenarios. Parameterize scripts to handle different data sets and dynamic values. | Completed
6 | Test Execution (Execute test) | Run performance tests in a controlled manner, gradually increasing the load to observe how the system behaves. Monitor key performance indicators (KPIs) like response time, throughput, CPU, memory usage, etc. | Completed
7 | Monitoring and Analysis | Collect and analyze performance data during test execution. Identify bottlenecks, slow response times, and resource constraints. | Completed
8 | Tuning and Optimization | Work with development and operations teams to address identified performance issues. Optimize code, database queries, configurations, and infrastructure as needed. | Completed
9 | Retesting | Re-run performance tests to verify the effectiveness of optimizations. Ensure that changes have resolved performance issues without introducing new ones. | Completed
10 | Reporting | Document test results, including metrics, observations, and identified issues. Provide detailed reports to stakeholders, highlighting areas that need improvement. | Completed
11 | Continuous Monitoring | Implement continuous performance monitoring in the production environment. Regularly review and refine performance tests to accommodate application updates and changing usage patterns. | Completed

## 1
Phase | Description | Details
Requirement Gathering & Analysis | Identify performance goals, including response times, throughput, and resource utilization. Understand the application's architecture, user load, and expected usage patterns. | Perforamcne Requirements/Performance Metrics: Response Time < 2 Throughput > 100 Error rate < 1% User Load: 1000 concurrent users Resource Utilization: CPU usage < 75%, Memory usage < 70%, Disk I/o > 600 per sec | collect details from NFR document/ BRD
Notes
NFR : Non-functional Requirement Document
BRD : Business Requirement Document

## 2
Phase | Description | Details
Planning and Design (Plan and Design Performance Tests) | Create a performance test plan outlining the scope, objectives, testing approach, and environment setup. Define performance test scenarios and workload models based on user behavior. | Summary Application Architecture Performance Test Requirements Performance Test Planning Performacnce Test Execution Note: Refer to Performance Test plan Template for Details & Understand how to prepare and what to include in performance test plan.

## 3
Phase | Description | Details
Environment Setup | Prepare the test environment, ensuring it mirrors the production environment as closely as possible. Configure necessary hardware, software, and network settings. | Refer to tables below
Notes:
1. * Details provided above are for illustration & learning purpose only, for your project you need collect actual environment details from related stake holders like : Business Analsyts, Developers, Functional Testing team, Automation Testing team
2. Test environment should be Subset of production system with few servers with same or lower specification
3. Test environment needs to be replica of production system, or it should be closer to production system in terms of configuration and resources
Table A
| Possible Options for Test environment Setup | Notes
1 | Make exact replica of production environment | complete image of production environment to duplicate to test environment
2 | Build a real environment from scratch
3 | Use production environment ** | backup product data, disable 3rd party apps, stubs
Table B
| Performance Test Environment Setup (Some common things to consider) | Notes
1 | Replicate Production Environment | Ensure hardware, software, network settings, and configurations match the production setup as closely as possible. Example: Use the same server specifications, operating system versions, and middleware configurations.
2 | Network Configuration | Match the network topology, bandwidth, and latency to the production environment. Example: Simulate network conditions such as firewalls, load balancers, and proxies.
3 | Database Setup | Use a database with similar size and schema to the production database. Example: Populate the database with the same volume of data and structure as production.
4 | Environment Isolation | Ensure the test environment is isolated from development and production to avoid interference. Example: Use a separate network segment and dedicated servers for the performance test environment.
5 | Monitoring and Logging Setup | Implement monitoring and logging tools to track performance metrics and identify bottlenecks. Example: Use tools like Grafana and Prometheus to monitor CPU, memory, disk I/O, and network usage.
Table C
# | Particulars | Details* (Test Environment) | Production Environment
1 | Environment Name | Production-like Test Environment | Production Environment
2 | Purpose | Performance Testing Phase 1 | Production Environment
3 | Application Under Test | E-commerce Website | E-commerce Website
4 | Application URL | https://petstore.octoperf.com/ | https://petstore.octoperf.com/
5 | Software | Application Server: Apache Tomcat 9.0.48 | Application Server: Apache Tomcat 9.0.48
6 |  | Database Server: MySQL 8.0.26 | Database Server: MySQL 8.0.26
7 |  | Load Generator: Apache JMeter 5.4.1 | Load Generator: Apache JMeter 5.4.1
8 | Hardware | Application Server: 4 CPU cores, 16 GB RAM | Application Server: 4 CPU cores, 16 GB RAM
9 |  | Web Server: 4 CPU cores, 16 GB RAM | Web Server: 4 CPU cores, 16 GB RAM
10 |  | Database Server: 4 CPU cores, 16 GB RAM | Database Server: 4 CPU cores, 16 GB RAM
11 | Network | Network Bandwidth: 1 Gbps | Network Bandwidth: 1 Gbps
12 |  | Latency: <5 ms | Latency: <5 ms
13 | Performance Monitoring Tools | Refer to : Table A | Refer to : Table A
15 | Security | SSL/TLS Enabled | SSL/TLS Enabled
16 |  | Firewall Rules: Port 443 open for HTTPS | Firewall Rules: Port 443 open for HTTPS
Table D
Server perforamnce monitoring tools
| Native Tools | Cloud based Tools
Web Server | Apache HTTP Server-mod_status | New Relic, Datadog, Dynatrace
Application Server | Apache Tomcat-Tomcat Manager | AppDynamics, Azure Application Insights, Dynatrace
Database Server | MySQL-MySQL Enterprise Monitor | Amazon CloudWatch, Datadog APM for Databases, SolarWinds Database Performance Monitor

## 4
Phase | Description | Details
Tool Selection | Choose appropriate performance testing tools (e.g., JMeter, LoadRunner, Gatling) based on the application and testing requirements. | Parameters to consider for tool selection: Type of Application Protocol Support Scalability Ease of Use Team skillset Integration with CI/CD Monitoring and Reporting Cost Community and Support Compatibility with Different Environments/OS
Server perforamnce monitoring tools
| Native Tools | Cloud based Tools
Web Server | Apache HTTP Server-mod_status | New Relic, Datadog, Dynatrace
Application Server | Apache Tomcat-Tomcat Manager | AppDynamics, Azure Application Insights, Dynatrace
Database Server | MySQL-MySQL Enterprise Monitor | Amazon CloudWatch, Datadog APM for Databases, SolarWinds Database Performance Monitor

## 5
Phase | Description | Details
Test Script Development (Implement Test ) | Develop performance test scripts simulating user actions and load scenarios. Parameterize scripts to handle different data sets and dynamic values. | Common Steps: Create Test Plan Record script using HTTP(S) test script recorder Add thread group & load Add samplers Add config elements Add Listeners Add Timers Add Logic controllers Add Assertions Add pre and post processors Do parameterization and co-relation
|  |  | Scenario# | Business Scenario | Step Number | Steps | Test Data | Parameterization | Co-relation
|  |  | Scenario 1 | Search | 1 | Open URL | https://petstore.octoperf.com/
[5 empty] | 2 | Key in Search value & Click on Search button |  | Yes
|  |  | Scenario 2 | View Details | 1 | Open URL | https://petstore.octoperf.com/
[5 empty] | 2 | Click on Category |  |  | Yes
[5 empty] | 3 | Click on Product ID |  |  | Yes
[5 empty] | 4 | Click on Item ID |  |  | Yes
|  |  | Scenario 3 | Add to Cart | 1 | Open URL | https://petstore.octoperf.com/
[5 empty] | 2 | Click on Sign In
[5 empty] | 3 | Enter user name and password, Click on Login | user name: test11, password: test11 | Yes
[5 empty] | 4 | Click on Category |  |  | Yes
[5 empty] | 5 | Click on Product ID |  |  | Yes
[5 empty] | 6 | Click on Add to Cart
[5 empty] | 7 | Click on Sign Out
|  |  | Scenario 4 | Checkout | 1 | Open URL | https://petstore.octoperf.com/
[5 empty] | 2 | Click on Sign In
[5 empty] | 3 | Enter user name and password, Click on Login |  | Yes
[5 empty] | 4 | Click on Category |  |  | Yes
[5 empty] | 5 | Click on Product ID |  |  | Yes
[5 empty] | 6 | Click on Add to Cart
[5 empty] | 7 | Click on Proceed to checkout
[5 empty] | 8 | Key in payment details and click continue
[5 empty] | 9 | Click on Confirm
[5 empty] | 10 | Click on Sign Out

## 6
Phase | Description | Details
Test Execution | Run performance tests in a controlled manner, gradually increasing the load to observe how the system behaves. Monitor key performance indicators (KPIs) like response time, throughput, CPU, memory usage, etc.
Table A
Before Starting the Performance Test Execution
# | Checklist of Tasks | Status
1 | Ensure test Environment is ready and stable | Done
2 | Ensure Test Data is ready | Done
3 | Use different user in each thread group | Done
4 | Verify parameterization is completed correctly | Done
5 | Verify co-relation is completed correctly | Done
6 | Unit test (test individual script) | Done
7 | Integration & Smoke Testing (Execute all scripts together with 1 to 10 users) | Done
Table B
| Performance Testing to be done | Possible Thread Group to be used | Notes
| Load Test | Ultimate Thread Group | Provides more control over the ramp-up and ramp-down of threads, allowing for complex load patterns. We can control number of users But we have no control over number of hits.
|  | Concurrency Thread Group | Allows you to specify the target number of concurrent users and maintain that load. We can control number users/threads. We do not have option to specify number of hits.
|  | Stepping Thread Group | Useful for gradually increasing the load and monitoring performance at different levels.
|  | Open Model Thread Group | Useful to achieve number of hits per/sec or min or hour. We have no option to specify number of users. It will simulate sudden increase in traffic (bursty traffic)
|  | Arrival Thread Group | Useful for scenarios where you want to simulate the arrival rate of users rather than a fixed number of concurrent users. This thread group allows you to model more realistic user behavior, especially in situations where the number of users arriving at the system over time is a critical factor. We can achieve Gradual increase or decrease in users. We can use this when we know the number of hits to be achieved. User load will be automatically taken care by this thread group.
| Stress Test | Ultimate Thread Group/Stepping Thread Group | Involves creating scenarios where your application is subjected to extreme conditions to identify its breaking points and observe how it performs under maximum load.
| Endurance(soak) Test | Ultimate Thread Group/ Arrival Thread Group | Run the test with normal load for longer duration such as 8 hours to 24 hours
|  |  |  | Cycle | Run | Scenario | Load Testing | Stress Testing | Spike Testing | Endurance Testing | Comments
|  |  |  | 1 | 1 | Scenario 1 (Load Testing) | ✔️ |  |  |  | Initial run for load testing
|  |  |  | 1 | 2 | Scenario 1 (Stress Testing) |  | ✔️ |  |  | Initial run for stress testing
|  |  |  | 1 | 3 | Scenario 1 (Spike Testing) |  |  | ✔️ |  | Initial run for spike testing
|  |  |  | 1 | 4 | Scenario 1 (Endurance Testing) |  |  |  | ✔️ | Initial run for endurance testing
|  |  |  | 1 | 5 | Scenario 2 (Load Testing) | ✔️ |  |  |  | Initial run for load testing
|  |  |  | 1 | 6 | Scenario 2 (Stress Testing) |  | ✔️ |  |  | Initial run for stress testing
|  |  |  | 1 | 7 | Scenario 2 (Spike Testing) |  |  | ✔️ |  | Initial run for spike testing
|  |  |  | 1 | 8 | Scenario 2 (Endurance Testing) |  |  |  | ✔️ | Initial run for endurance testing
|  |  |  | 2 | 1 | Scenario 3 (Load Testing) | ✔️ |  |  |  | Second cycle for load testing
|  |  |  | 2 | 2 | Scenario 3 (Stress Testing) |  | ✔️ |  |  | Second cycle for stress testing
|  |  |  | 2 | 3 | Scenario 3 (Spike Testing) |  |  | ✔️ |  | Second cycle for spike testing
|  |  |  | 2 | 4 | Scenario 3 (Endurance Testing) |  |  |  | ✔️ | Second cycle for endurance testing
|  |  |  | 2 | 5 | Scenario 4 (Load Testing) | ✔️ |  |  |  | Second cycle for load testing
|  |  |  | 2 | 6 | Scenario 4 (Stress Testing) |  | ✔️ |  |  | Second cycle for stress testing
|  |  |  | 2 | 7 | Scenario 4 (Spike Testing) |  |  | ✔️ |  | Second cycle for spike testing
|  |  |  | 2 | 8 | Scenario 4 (Endurance Testing) |  |  |  | ✔️ | Second cycle for endurance testing

## 7
Phase | Description | Details
Monitoring and Analysis | Collect and analyze performance data during test execution. Identify bottlenecks, slow response times, and resource constraints.
Test Summary
|  |  | Total test duration: 2.5 hours | [Ramp up : 15 mins , Steady State: 120 mins, Ramp down:15 mins]
Total virtual users: 500
Total requests sent: 12000
Test Environment: Pre-production
Test type: Load test
|  |  | Execution cycle : 1 | [ we need to run 3-4 cycle of run with same setup and compare the results]
Response Time Summary
Script 1: Search
|  |  |  | Step Number | Transaction | Throughput (Transactions processed per second) | Min Response Time (Sec) | Max Response Time (Sec) | Median Response Time (Sec) | Average Response Time (Sec) | Total Hits | Pass Transaction Percentage | Failed Transaction Percentage
|  |  |  | 1 | Open Url | 13.3 | 0.8 | 2.7 | 1.2 | 1.26 | 1331 | 100% | 0%
|  |  |  | 2 | Search | 13.42 | 0.1 | 2.6 | 0.36 | 0.424 | 1316 | 100% | 0%
Script 2: View Details
|  |  |  | Step Number | Transaction | Throughput (Transactions processed per second) | Min Response Time (Sec) | Max Response Time (Sec) | Median Response Time (Sec) | Average Response Time (Sec) | Total Hits | Pass Transaction Percentage | Failed Transaction Percentage
|  |  |  | 1 | Open Url | 13.32 | 0.83 | 2.72 | 1.15 | 1.23 | 300 | 100% | 0%
|  |  |  | 2 | Click on Category | 2.98 | 0.1 | 5.6 | 0.35 | 0.48 | 288 | 100% | 0%
|  |  |  | 3 | Click on Product Id | 3.02 | 0.1 | 0.94 | 0.34 | 0.39 | 266 | 100% | 0%
|  |  |  | 4 | Click on Item Id | 2.97 | 0.1 | 1.39 | 0.34 | 0.38 | 250 | 100% | 0%
Script 3: Add to cart
|  |  |  | Step Number | Transaction | Throughput (Transactions processed per second) | Min Response Time (Sec) | Max Response Time (Sec) | Median Response Time (Sec) | Average Response Time (Sec) | Total Hits | Pass Transaction Percentage | Failed Transaction Percentage
|  |  |  | 1 | Open Url | 10.11 | 0.89 | 2.09 | 1.19 | 1.78 | 48 | 100% | 0%
|  |  |  | 2 | Click on Sign in | 8.2 | 0.1 | 0.73 | 0.31 | 0.76 | 47 | 100% | 0%
|  |  |  | 3 | Key in user name and password click Login | 7.5 | 0.1 | 5.9 | 0.82 | 1.12 | 44 | 100% | 0%
|  |  |  | 4 | Click on Category | 7.1 | 0.1 | 0.6 | 0.4 | 0.57 | 21 | 100% | 0%
|  |  |  | 5 | Click on Product Id | 6.6 | 0.1 | 0.53 | 0.4 | 0.51 | 39 | 100% | 0%
|  |  |  | 6 | Click on Add to Cart | 6.2 | 0.1 | 0.7 | 0.37 | 0.42 | 36 | 100% | 0%
|  |  |  | 7 | Click on Sign Out | 5.1 | 0.27 | 0.82 | 0.39 | 0.45 | 33
Script 3: Checkout
|  |  |  | Step Number | Transaction | Throughput (Transactions processed per second) | Min Response Time (Sec) | Max Response Time (Sec) | Median Response Time (Sec) | Average Response Time (Sec) | Total Hits | Pass Transaction Percentage | Failed Transaction Percentage
|  |  |  | 1 | Open Url | 10.11 | 0.86 | 1.15 | 1.09 | 1.09 | 4 | 100% | 0%
|  |  |  | 2 | Click on Sign in | 8.2 | 0.1 | 0.32 | 0.32 | 0.27 | 3 | 100% | 0%
|  |  |  | 3 | Key in user name and password click Login | 7.5 | 0.63 | 0.63 | 0.63 | 0.63 | 2 | 100% | 0%
|  |  |  | 4 | Click on Category | 7.1 | 0.32 | 0.32 | 0.32 | 0.32 | 2 | 100% | 0%
|  |  |  | 5 | Click on Product Id | 6.6 | 0.39 | 0.39 | 0.39 | 0.39 | 2 | 100% | 0%
|  |  |  | 6 | Click on Add to Cart | 6.2 | 0.28 | 0.28 | 0.28 | 0.28 | 2 | 100% | 0%
|  |  |  | 7 | Click on Proceed to Checkout | 6.1 | 0.42 | 0.42 | 0.42 | 0.42 | 2 | 100% | 0%
|  |  |  | 8 | Key in payment details and click continue | 5.9 | 0.32 | 0.32 | 0.32 | 0.32 | 2 | 100% | 0%
|  |  |  | 9 | Click on Confirm | 5.6 | 0.42 | 0.42 | 0.42 | 0.42 | 2 | 100% | 0%
|  |  |  | 10 | Click on Signout | 5.2 | 1.55 | 1.55 | 1.55 | 1.02 | 2 | 100% | 0%
CPU, Memory, Network Bandwidth Utilization
|  |  |  | Metric | Web Server ( Server 1) | Application Server (Server 2) | Database Server Server 3)
|  |  |  | Mimimum Memory Utilization | 12% | 15% | 18%
|  |  |  | Maximum Memory Utilization | 50% | 60% | 70%
|  |  |  | Average Memory Utilization | 36% | 42% | 49%
|  |  |  | Mimimum CPU Utilization | 45% | 48% | 50%
|  |  |  | Maximum CPU Utilization | 78% | 82% | 84%
|  |  |  | Average CPU Utilization | 68% | 70% | 72%
|  |  |  | Mimimum Network Utilization | 110 KB/Sec | 125 KB/Sec | 128 KB/Sec
|  |  |  | Maximum Network Utilization | 190 KB/Sec | 222 KB/Sec | 225 KB/Sec
|  |  |  | Average Network Utilization | 160 KB/Sec | 175 KB/Sec | 188 KB/Sec

## 8
Phase | Description | Details
Tuning and Optimization | Work with development and operations teams to address identified performance issues. Optimize code, database queries, configurations, and infrastructure as needed. | This phase focuses on making necessary adjustments to improve system performance. We need to coordinate with development and infrastructure team to make any changes that may be required.
Key Objectives | -> Identify and resolve performance bottlenecks. -> Optimize application code, database queries, and configurations. -> Ensure the system meets performance requirements under expected load conditions.
Steps in Tuning and Optimization
1 | Analyze Collected Data | Review performance test results to identify slow response times, high resource utilization, and other performance issues. Use monitoring tools to analyze CPU, memory, disk I/O, and network usage.
2 | Identify Bottlenecks | Look for patterns indicating bottlenecks, such as a specific function or query causing delays. Common bottlenecks include inefficient code, slow database queries, limited server resources, and network latency.
3 | Optimize Code | Refactor inefficient code to reduce execution time. Example: Replace nested loops with more efficient algorithms.
4 | Database Optimization | Optimize SQL queries and indexes to speed up database operations. Example: Add indexes to frequently queried columns to reduce query execution time.
5 | Configuration Tuning | Adjust server and application configurations to improve performance. Example: Increase the heap size of a Java application to prevent frequent garbage collection pauses.
6 | Infrastructure Scaling | Scale infrastructure vertically (adding more resources to existing servers) or horizontally (adding more servers) based on the load. Example: Add more instances to a load balancer to distribute traffic evenly.

## 9
Phase | Description | Details
Retesting | Re-run performance tests to verify the effectiveness of optimizations. Ensure that changes have resolved performance issues without introducing new ones.
Key Objectives | -> Validate the effectiveness of performance improvements. -> Ensure that the system still meets performance requirements. -> Detect any new issues introduced by changes. |  | Cycle | Run | Scenario | Load Testing | Stress Testing | Spike Testing | Endurance Testing | Comments
|  |  | 1 | 1 | Scenario 1 (Load Testing) | ✔️ |  |  |  | Initial run for load testing
Steps in Retesting |  |  | 1 | 2 | Scenario 1 (Stress Testing) |  | ✔️ |  |  | Initial run for stress testing
1 | Re-run Performance Tests | Execute the same performance tests that were initially run to identify performance issues. Use the same test scripts, scenarios, and load conditions to ensure consistency. | 1 | 3 | Scenario 1 (Spike Testing) |  |  | ✔️ |  | Initial run for spike testing
2 | Compare Results | Compare the new test results with the baseline results (results from initial testing before optimization). Look for improvements in key performance indicators (KPIs) such as response times, throughput, and resource utilization. | 1 | 4 | Scenario 1 (Endurance Testing) |  |  |  | ✔️ | Initial run for endurance testing
3 | Verify Fixes | Ensure that the specific issues identified during initial testing have been resolved. Check that the optimizations have had the desired effect on system performance. | 1 | 5 | Scenario 2 (Load Testing) | ✔️ |  |  |  | Initial run for load testing
4 | Check for Regression | Ensure that the changes have not introduced new performance issues. Conduct a thorough analysis to identify any new bottlenecks or degraded performance in other areas. | 1 | 6 | Scenario 2 (Stress Testing) |  | ✔️ |  |  | Initial run for stress testing
5 | Validate Under Different Load Conditions | Test the application under different load conditions, including peak load and stress conditions. Ensure that the system performs well under all expected usage scenarios. | 1 | 7 | Scenario 2 (Spike Testing) |  |  | ✔️ |  | Initial run for spike testing
6 | Monitor System Behavior | Use monitoring tools to observe system behavior during retesting. Pay attention to CPU, memory, disk I/O, and network usage to identify any potential issues. | 1 | 8 | Scenario 2 (Endurance Testing) |  |  |  | ✔️ | Initial run for endurance testing
7 | Document Results | Record the new performance metrics and compare them with the baseline. Document any remaining issues or areas for further optimization. | 2 | 1 | Scenario 3 (Load Testing) | ✔️ |  |  |  | Second cycle for load testing
|  |  | 2 | 2 | Scenario 3 (Stress Testing) |  | ✔️ |  |  | Second cycle for stress testing
|  |  | 2 | 3 | Scenario 3 (Spike Testing) |  |  | ✔️ |  | Second cycle for spike testing
|  |  | 2 | 4 | Scenario 3 (Endurance Testing) |  |  |  | ✔️ | Second cycle for endurance testing
|  |  | 2 | 5 | Scenario 4 (Load Testing) | ✔️ |  |  |  | Second cycle for load testing
|  |  | 2 | 6 | Scenario 4 (Stress Testing) |  | ✔️ |  |  | Second cycle for stress testing
|  |  | 2 | 7 | Scenario 4 (Spike Testing) |  |  | ✔️ |  | Second cycle for spike testing
|  |  | 2 | 8 | Scenario 4 (Endurance Testing) |  |  |  | ✔️ | Second cycle for endurance testing

## 10
Phase | Description | Details
Reporting | -> Document test results, including metrics, observations, and identified issues. -> Provide detailed reports to stakeholders, highlighting areas that need improvement. | -> It involves documenting and presenting the findings of the performance tests to stakeholders. -> Clear and comprehensive reports help stakeholders understand the system’s performance and make informed decisions.
|  |  | Section | Description
|  |  | Executive Summary | Objective: Ensure the application can handle 500 concurrent users. Key Findings: The application meets performance criteria with an average response time of 2 seconds.
|  |  | Test Objectives and Scope | Objectives: Assess the performance of the view product, Search, Add to cart, chechkout functionalities. Scope: Tested under normal and peak load conditions.
|  |  | Test Environment | Environment: 2 web servers, 1 Aplication server, 1 database server, simulated network conditions. CPU, Memory etc
|  |  | Test Scenarios and Workloads | Scenarios: Search,View, Add to cart, checkout Workloads: 500 concurrent users for 2 hours.
|  |  | Key Performance Metrics | Response Time: Average 2 seconds. Throughput: 300 transactions per minute. Resource Utilization: CPU at 70%, Memory at 60%.
|  |  | Test Results | View : Average response time= 2 sec, No error Search: Average response time= 2 sec, No error Add to cart: Average response time= 2 sec, No error Checkout : Average response time= 2 sec, 0.5% error
|  |  | Analysis and Findings | Identified bottleneck in the checkout process due to database query inefficiencies. CPU and memory usage within acceptable limits.
|  |  | Recommendations | Optimize database queries for the checkout process. Consider increasing database server capacity for peak loads.
|  |  | Conclusion | The application performs well under normal load but needs optimization for peak load scenarios.
|  |  | Appendices | Include raw test data, scripts used, and detailed configuration information.
Test Summary
Total test duration: 2.5 hours | [Ramp up : 15 mins , Steady State: 120 mins, Ramp down:15 mins]
Total virtual users: 500
Total requests sent: 12000
Test Environment: Pre-production
Test type: Load test
Execution cycle : 1 | [ we need to run 3-4 cycle of run with same setup and compare the results]
Response Time Summary
Script 1: Search
|  | Step Number | Transaction | Throughput (Transactions processed per second) | Min Response Time (Sec) | Max Response Time (Sec) | Median Response Time (Sec) | Average Response Time (Sec) | Total Hits | Pass Transaction Percentage | Failed Transaction Percentage
|  | 1 | Open Url | 13.3 | 0.8 | 2.7 | 1.2 | 1.26 | 1331 | 1 | 0
|  | 2 | Search | 13.42 | 0.1 | 2.6 | 0.36 | 0.424 | 1316 | 1 | 0
Script 2: View Details
|  | Step Number | Transaction | Throughput (Transactions processed per second) | Min Response Time (Sec) | Max Response Time (Sec) | Median Response Time (Sec) | Average Response Time (Sec) | Total Hits | Pass Transaction Percentage | Failed Transaction Percentage
|  | 1 | Open Url | 13.32 | 0.83 | 2.72 | 1.15 | 1.23 | 300 | 1 | 0
|  | 2 | Click on Category | 2.98 | 0.1 | 5.6 | 0.35 | 0.48 | 288 | 1 | 0
|  | 3 | Click on Product Id | 3.02 | 0.1 | 0.94 | 0.34 | 0.39 | 266 | 1 | 0
|  | 4 | Click on Item Id | 2.97 | 0.1 | 1.39 | 0.34 | 0.38 | 250 | 1 | 0
Script 3: Add to cart
|  | Step Number | Transaction | Throughput (Transactions processed per second) | Min Response Time (Sec) | Max Response Time (Sec) | Median Response Time (Sec) | Average Response Time (Sec) | Total Hits | Pass Transaction Percentage | Failed Transaction Percentage
|  | 1 | Open Url | 10.11 | 0.89 | 2.09 | 1.19 | 1.78 | 48 | 1 | 0
|  | 2 | Click on Sign in | 8.2 | 0.1 | 0.73 | 0.31 | 0.76 | 47 | 1 | 0
|  | 3 | Key in user name and password click Login | 7.5 | 0.1 | 5.9 | 0.82 | 1.12 | 44 | 1 | 0
|  | 4 | Click on Category | 7.1 | 0.1 | 0.6 | 0.4 | 0.57 | 21 | 1 | 0
|  | 5 | Click on Product Id | 6.6 | 0.1 | 0.53 | 0.4 | 0.51 | 39 | 1 | 0
|  | 6 | Click on Add to Cart | 6.2 | 0.1 | 0.7 | 0.37 | 0.42 | 36 | 1 | 0
|  | 7 | Click on Sign Out | 5.1 | 0.27 | 0.82 | 0.39 | 0.45 | 33
Script 3: Checkout
|  | Step Number | Transaction | Throughput (Transactions processed per second) | Min Response Time (Sec) | Max Response Time (Sec) | Median Response Time (Sec) | Average Response Time (Sec) | Total Hits | Pass Transaction Percentage | Failed Transaction Percentage
|  | 1 | Open Url | 10.11 | 0.86 | 1.15 | 1.09 | 1.09 | 4 | 1 | 0
|  | 2 | Click on Sign in | 8.2 | 0.1 | 0.32 | 0.32 | 0.27 | 3 | 1 | 0
|  | 3 | Key in user name and password click Login | 7.5 | 0.63 | 0.63 | 0.63 | 0.63 | 2 | 1 | 0
|  | 4 | Click on Category | 7.1 | 0.32 | 0.32 | 0.32 | 0.32 | 2 | 1 | 0
|  | 5 | Click on Product Id | 6.6 | 0.39 | 0.39 | 0.39 | 0.39 | 2 | 1 | 0
|  | 6 | Click on Add to Cart | 6.2 | 0.28 | 0.28 | 0.28 | 0.28 | 2 | 1 | 0
|  | 7 | Click on Proceed to Checkout | 6.1 | 0.42 | 0.42 | 0.42 | 0.42 | 2 | 1 | 0
|  | 8 | Key in payment details and click continue | 5.9 | 0.32 | 0.32 | 0.32 | 0.32 | 2 | 1 | 0
|  | 9 | Click on Confirm | 5.6 | 0.42 | 0.42 | 0.42 | 0.42 | 2 | 1 | 0
|  | 10 | Click on Signout | 5.2 | 1.55 | 1.55 | 1.55 | 1.02 | 2 | 1 | 0
| CPU, Memory, Network Bandwidth Utilization | Metric | Web Server ( Server 1) | Application Server (Server 2) | Database Server Server 3)
|  | Mimimum Memory Utilization | 0.12 | 0.15 | 0.18
|  | Maximum Memory Utilization | 0.5 | 0.6 | 0.7
|  | Average Memory Utilization | 0.36 | 0.42 | 0.49
|  | Mimimum CPU Utilization | 0.45 | 0.48 | 0.5
|  | Maximum CPU Utilization | 0.78 | 0.82 | 0.84
|  | Average CPU Utilization | 0.68 | 0.7 | 0.72
|  | Mimimum Network Utilization | 110 KB/Sec | 125 KB/Sec | 128 KB/Sec
|  | Maximum Network Utilization | 190 KB/Sec | 222 KB/Sec | 225 KB/Sec
|  | Average Network Utilization | 160 KB/Sec | 175 KB/Sec | 188 KB/Sec

## 11
Phase | Description | Details
Continuous Monitoring | ->Implement continuous performance monitoring in the production environment. -> Regularly review and refine performance tests to accommodate application updates and changing usage patterns. | It involves ongoing observation and analysis of the application's performance in the production environment to ensure it meets performance standards and to detect issues proactively.
Key Objectives | 1. Monitor the application’s performance in real-time. 2. Detect and address performance issues before they impact users. 3. Ensure the system maintains optimal performance under varying loads.
Steps
1 | Setting Up Monitoring Tools | -> Choose appropriate monitoring tools (e.g., New Relic, Dynatrace, AppDynamics) based on application requirements. -> Configure tools to monitor key performance metrics such as response times, throughput, error rates, and resource utilization (CPU, memory, disk I/O, network).
2 | Defining Key Performance Indicators (KPIs) | -> Identify and define KPIs that are critical for the application’s performance. -> Common KPIs include average response time, peak response time, request rate, error rate, CPU usage, memory usage, and disk I/O.
3 | Establishing Baselines and Thresholds | -> Establish performance baselines from historical data or initial test results. -> Set thresholds for KPIs to trigger alerts when performance deviates from expected norms.
4 | Real-time Monitoring and Alerts | -> Continuously monitor the application’s performance in real-time. -> Set up automated alerts to notify the team of any performance issues or threshold breaches.
5 | Analyzing Performance Data | -> Regularly review and analyze performance data to identify trends, patterns, and potential issues. -> Use historical data to predict future performance and capacity planning.
6 | Proactive Issue Resolution | -> Investigate and resolve performance issues promptly to minimize impact on users. -> Collaborate with development and operations teams to address root causes and implement fixes.
7 | Reporting and Documentation | -> Generate regular performance reports to provide insights into the application’s health. -> Document any issues identified and actions taken to resolve them.